## Startup Project Gantt Chart
| Company Address Company Email Company Website Company Number | 20% | [9 empty] | STARTUP PROJECT GANTT CHART
|  |  |  | Project Status Summary |  |  | - SELECT YEAR -
|  |  |  | Completed | 2 |  | 2024-01-01
|  | COMPLETION RATE |  | In Progress | 1
|  |  |  | Not Started | 7
P R O J E C T | T A S K | A S S I G N E D T O | S T A R T D A T E | E N D D A T E | D U R A T I O N | P R O G R E S S |  | S T A T U S | 1st Quarter | [90 empty] | 2nd Quarter | [90 empty] | 3rd Quarter | [91 empty] | 4th Quarter
[9 empty] | 2024-01-01 | [30 empty] | 2024-02-01 | [28 empty] | 2024-03-01 | [30 empty] | 2024-04-01 | [29 empty] | 2024-05-01 | [30 empty] | 2024-06-01 | [29 empty] | 2024-07-29 | [30 empty] | 2024-08-27 | [30 empty] | 2024-09-25 | [29 empty] | 2024-10-24 | [30 empty] | 2024-11-22 | [29 empty] | 2024-12-21
 | time axis 2024-01-01 to 2024-12-31
Research & Planning | [6 empty] | 0%
Market Analysis | Conduct Market Research | Sarah Johnson | 2024-01-01 | 2024-01-15 | 15 | 88% | 88% | Completed
Business Planning | Develop Business Plan | Robert Miller | 2024-01-16 | 2024-01-31 | 16 | 80% | 80% | Completed
Product Development
Design | Create Product Design | Olivia Taylor | 2024-02-01 | 2024-02-28 | 28 | 60% | 60% | In Progress
Prototyping | Build Prototype | Olivia Taylor | 2024-03-01 | 2024-03-31 | 31 |  | 0% | Not Started
Testing | Conduct Testing | James Anderson | 2024-04-01 | 2024-04-15 | 15 |  | 0% | Not Started
Iteration | Make Improvements | Emma Turner | 2024-04-16 | 2024-04-30 | 15 |  | 0% | Not Started
Final Development | Finalize Product | Daniel Clark | 2024-05-01 | 2024-05-31 | 31 |  | 0% | Not Started
Marketing
Strategy Development | Develop Marketing Strategy | Mia Garcia | 2024-06-01 | 2024-06-15 | 15 |  | 0% | Not Started
Pre-Launch Preparation | Prepare for Launch | Liam Parker | 2024-06-16 | 2024-06-30 | 15 |  | 0% | Not Started
Launch
Launch Event | Execute Product Launch | Sophia Lee | 2024-07-01 | 2024-07-01 | 1 |  | 0% | Not Started
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
Note on G8: Manually input the Details for the Task/Milestone Name, Start and End Dates.
Note on H8: Duration is AUTOMATED based on the Start and End Dates.
Note on K8: Select the Status of the task where the dropdown list is editable in the Setup sheet.

## Sheet3 (hidden)
10 | 20%
80%

## Employee Information
Full Name | Address | Contact Number | Email
Sarah Johnson | 567 Tech Blvd, Cityville | (555) 111-2222 | name@email.com
Robert Miller | 123 Market St, Townsville | (555) 333-4444 | name@email.com
Olivia Taylor | 789 Code Lane, Villageton | (555) 555-6666 | name@email.com
James Anderson | 456 HR Ave, Hamletown | (555) 777-8888 | name@email.com
Emma Turner | 987 Art Street, Borough | (555) 999-0000 | name@email.com
Daniel Clark | 321 Data Drive, Cityville | (555) 111-3333 | name@email.com
Sophia Lee | 654 Sales Street, Townsville | (555) 222-4444 | name@email.com
Ethan Brown | 789 Help Lane, Villageton | (555) 333-5555 | name@email.com
Mia Garcia | 101 Finance Ave, Hamletown | (555) 444-6666 | name@email.com
Liam Parker | 246 Design Blvd, Borough | (555) 555-7777 | name@email.com

## Setup
S E T U P
STATUS
Completed
Not Started
In Progress

## Helper (hidden)
2024-01-01
2025-01-01
2026-01-01
2027-01-01
2028-01-01
2029-01-01
2030-01-01
2031-01-01
2032-01-01
2033-01-01
2034-01-01
2035-01-01
2036-01-01
2037-01-01
2038-01-01
2039-01-01
2040-01-01